## Feuille1
Planning and Recipe
(one document per team)
The aim of this doc is to define as precisely as possible the tasks and the "what to do" planning. Fill all the red sections.
Project Title | POC datawarehouse Big Data
Project Number | Project 203
Team Referent | Anthony Gregori
Other Team Members | Elies Hilali, Raméz Aissaoui, Maxime Stojanovic
Team Mentor | My first and last name, Email
Project Partner | Acensi |  | Fabrice Dufour |  | fabrice.dufour@acensi.fr
Planning | [6 empty] | Risks Management |  | Skills |  | Recipe
Tasks | Starting Date | Duration | Deadline | Responsable | Who realise | Ressources | Risks | Action if necessary | Used | Acquired | Validation criteria | Success | If not : justification and solution
Study of the Subject | 2016-10-10 | 30-45 days | 2016-11-15 | Anthony | Ramez, Elies, Maxime | study from the former group |  |  | Comunicate with the team/company
- What are the diferents solutions ? |  |  |  | Elies
- Study of concurrence |  |  |  | Maxime
Tests of all the solutions | 2016-11-15 | around 1 month | 2016-12-10 | Anthony | Ramez, Elies, Maxime | From the Web
Prepare the review | 2016-11-25 |  | 2016-12-13 |  | Ramez
First Project Review |  |  | 2016-12-13
Redefining the project after the tests | 2017-01-01 | around 1 month | 2017-02-01 | Anthony | Ramez, Elies, Maxime
Redefining the panning | 2017-01-01 |  |  | Anthony | Ramez, Elies, Maxime
To be Continued